## gabe - project board
Gabe - Project Board
Development
Name | Subitems | Person | Subitems Status | Subitems Timeline | Status | Date | Item ID (auto generated)
SOC Implementation & Virtual Lab
Name | Subitems | Person | Subitems Status | Subitems Timeline | Status | Date | Item ID (auto generated)
Lab Setup | Create virtual network lab (Linux, Windows, DMZ, firewall),Install and configure SIEM (Splunk or Elastic),Install Wireshark on network monitoring node,Enable audit logging on Windows or Linux,Validate lab functionality with test logins | Gabriel Zepeda | Working on it | 2025-07-07 - 2025-07-08, 2025-07-07 - 2025-07-09, 2025-07-09 - 2025-07-09, 2025-07-07 - 2025-07-10, 2025-07-10 - 2025-07-10 |  |  | 9402131559
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Item ID (auto generated)
| Create virtual network lab (Linux, Windows, DMZ, firewall) | Gabriel Zepeda | Working on it | 2025-07-07 | 2025-07-08 | 9404826560
| Install and configure SIEM (Splunk or Elastic) | Gabriel Zepeda |  | 2025-07-07 | 2025-07-09 | 9404834514
| Install Wireshark on network monitoring node | Gabriel Zepeda |  | 2025-07-09 | 2025-07-09 | 9404865752
| Enable audit logging on Windows or Linux | Gabriel Zepeda |  | 2025-07-07 | 2025-07-10 | 9404868472
| Validate lab functionality with test logins | Gabriel Zepeda |  | 2025-07-10 | 2025-07-10 | 9404870902
Research and Implement Attack Vectors | Launch brute force attack (e.g., Hydra),Simulate phishing payload delivery (email or dropper),Emulate privilege escalation (e.g., mimikatz),Conduct lateral movement (e.g., PsExec),Create ransomware/malicious file activity,Conduct network scanning (nmap),Trigger fileless attack (PowerShell scripts),Confirm all attacks are logged in SIEM,Develop Remediation Scripts and Playbook for each attack | Gabriel Zepeda |  | 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17, 2025-07-14 - 2025-07-17 |  |  | 9402131577
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Item ID (auto generated)
| Launch brute force attack (e.g., Hydra) | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404925650
| Simulate phishing payload delivery (email or dropper) | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404926849
| Emulate privilege escalation (e.g., mimikatz) | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404931393
| Conduct lateral movement (e.g., PsExec) | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404933604
| Create ransomware/malicious file activity | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404934247
| Conduct network scanning (nmap) | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404936248
| Trigger fileless attack (PowerShell scripts) | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404937056
| Confirm all attacks are logged in SIEM | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9404937878
| Develop Remediation Scripts and Playbook for each attack | Gabriel Zepeda |  | 2025-07-14 | 2025-07-17 | 9405636585
Detection, Investigation & Response | Identify IOCs in SIEM (hashes, IPs, file names),Triaging suspicious alerts,Investigate incident chain (kill chain mapping),Perform containment (block IPs, isolate host),Improve remediation scripts (restore, clean),Annotate SIEM logs with incident notes | Gabriel Zepeda |  | 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31 |  |  | 9402131585
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Item ID (auto generated)
| Identify IOCs in SIEM (hashes, IPs, file names) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9404952768
| Triaging suspicious alerts | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9404953904
| Investigate incident chain (kill chain mapping) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9404955085
| Perform containment (block IPs, isolate host) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9404956090
| Improve remediation scripts (restore, clean) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9404956972
| Annotate SIEM logs with incident notes | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9404957654
Forensics & Final Reporting | Analyze endpoint logs (PowerShell, Sysmon),Reconstruct attacker timeline (TTPs),Perform basic malware analysis (strings, behavior),Write detailed incident report,Conduct project debrief & lessons learned | Gabriel Zepeda |  | 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31, 2025-07-28 - 2025-07-31 |  |  | 9404662774
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Item ID (auto generated)
| Analyze endpoint logs (PowerShell, Sysmon) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9405093540
| Reconstruct attacker timeline (TTPs) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9405095372
| Perform basic malware analysis (strings, behavior) | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9405096856
| Write detailed incident report | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9405097920
| Conduct project debrief & lessons learned | Gabriel Zepeda |  | 2025-07-28 | 2025-07-31 | 9405098436
Group Title
Name | Subitems | Person | Subitems Status | Subitems Timeline | Status | Date | Item ID (auto generated)
Item 4 | [5 empty] | 2025-06-15 | 9402131600
Item 5 | [5 empty] | 2025-06-15 | 9402131592
2025-06-15

## gabe - project board-updates
Gabe - Project Board | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9402131559 | Lab Setup | Update |  | Gabriel Zepeda | 18/June/2025 01:29:05 PM | Success Goals - Working Virtual Environment (Virtual Lab) for testing - Installation of necessary software (Splunk, maps, Wireshark, etc) - Enable logging with my SIEM software - Ability to restore my Virtual Environment to a previous state | 0 |  | 4218033249